## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1525/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 14.35 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MATIKONA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE |  | ORD/000774/2022-2023 | 224/BSD | 08/06/2022 | 06/09/2022 | M/S R DUTTA & CO. | 4.99 | 0 | 0 | 100
3 | BIRBHUM | Illambazar | Bolpur Mechanical | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | New power connection at Matikona PWSS under Bolpur Mechanical Division.PHE.Dte. |  |  | BILL/00416/2024-2025 | BP-24-25-131 | 29/07/2024 | 29/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Central Drilling | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Illambazar | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 27/03/2026 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
6 | BIRBHUM | Illambazar | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME | SM/13643 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 23825.65 | 0 | 0