## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 2174/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 136.35 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Bolpur Mechanical | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | New | New service connection for Nohona PWSS (Block- Illambazar) |  |  | BILL/00136/2024-2025 | BP-2024-2025-55 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.61 | 0 | 0 | 0
3 | BIRBHUM | Illambazar | Birbhum Division | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 24/12/2026 | BIPIN KUMAR SINGH | 2395.67 | 105.15 | 4.39 | 4
4 | BIRBHUM | Illambazar | Bolpur Mechanical | NOHNA PIPED WATER SUPPLY SCHEME | SM/13645 | New | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000531/2023-2024 | 2172/Bol.MD | 01/09/2023 | 01/02/2025 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 3.47 | 23.22 | 80
Total | [13 empty] | 2551.59 | 108.62 | 4.26