## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Continuation Work Order for Preparation & Submission of DPR for (Nabagram) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000626/2022-2023 | 217/RSD | 21/06/2022 | 05/08/2022 | ECO CARE | 4 | 3.73 | 93.32 | 100
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 1554/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 26.05 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Birbhum Division | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 227/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 0.92 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Quotation for new service connection at Nabagram TW No-I (Block-Rampurhat-II) |  |  | BILL/02224/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Quotation for new service connection at Nabagram TW No-II (Block-Rampurhat-II) |  |  | BILL/02223/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.49 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | WBSEDCL QUOTATION FOR NABAGRAM TW-II |  |  | BILL/02246/2023-2024 | BP-2023-24-311 | 18/03/2024 | 18/03/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | WBSEDCL QUOTATION FOR NABAGRAM TW-1 |  |  | BILL/02249/2023-2024 | BP-2023-24-312 | 18/03/2024 | 18/03/2024 | WBSEDCL | 2.85 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-II | Birbhum Division | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 09/11/2025 | SUNIL RABI DAS | 1157.77 | 82.97 | 7.17 | 40
9 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Providing Electro-mechanical accessories and others for Nabagram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000481/2023-2024 | 2233/Bol.MD | 12/09/2023 | 01/07/2025 | M. S. ENTERPRISE | 45.35 | 17.18 | 37.89 | 80
10 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. | SM/13646 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Nabagram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001250/2023-2024 | 526/BOL.MD | 14/03/2024 | 01/04/2025 | MENAKA ENTERPRISE | 7.62 | 0 | 0 | 40
Total | [13 empty] | 1254.41 | 103.88 | 8.28