## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1527/BHM | 26/04/2023 |  | Resource Division | 19.61 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | AE |  | ORD/000777/2022-2023 | 311/BSD | 17/08/2022 | 15/11/2022 | M/S R DUTTA & CO. | 1.43 | 0.86 | 60.08 | 100
3 | BIRBHUM | Illambazar | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | AE |  | ORD/000776/2022-2023 | 284/BSD | 25/07/2022 | 23/10/2022 | M/S R DUTTA & CO. | 4.93 | 1.91 | 38.68 | 100
4 | BIRBHUM | Illambazar | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 17/05/2024 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
5 | BIRBHUM | Illambazar | Central Drilling | SHIRSHA PIPED WATER SUPPLY SCHEME | SM/13647 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 23761.41 | 2.77 | 0.01