## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sadanandapur piped water supply scheme. | SM/13648 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1548/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 9.67 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sadanandapur piped water supply scheme. | SM/13648 | New | Providing Electro-mechanical accessories and others for SADANANDAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000295/2023-2024 | 1500/Bol.MD | 17/07/2023 | 15/09/2023 | SATYAJIT GHOSH | 27.88 | 25.52 | 91.53 | 85
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sadanandapur piped water supply scheme. | SM/13648 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at sadanandapur W/S scheme (Asenga I & II) of Md. Bazar block under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2024-2025 | 769/BMSD(D) | 26/09/2024 | 26/10/2024 | DEY ENTERPRISE | 4.33 | 2.74 | 63.23 | 100
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sadanandapur piped water supply scheme. | SM/13648 | New | WBSEDCL QUOTATION FOR SADANANDAPUR PH NO-1 |  |  | BILL/01570/2023-2024 | BP-23-24-224 | 15/01/2024 | 15/01/2024 | WBSEDCL | 0.31 | 0 | 0 | 0
5 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sadanandapur piped water supply scheme. | SM/13648 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
Total | [13 empty] | 82.47 | 28.25 | 34.26