## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Sahapur Piped water Supply Scheme. | SM/13649 | New | Providing electro-mechanical accessories and others for Shapaur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000772/2022-2023 | 307/Bol.MD | 23/03/2023 | 23/03/2024 | A. G. ENTERPRISE | 93.34 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Sahapur Piped water Supply Scheme. | SM/13649 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 1556/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 138.02 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Sahapur Piped water Supply Scheme. | SM/13649 | New | Providing electro mechanical accessories and others for Sahapur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000784/2022-2023 | 319/Bol.MD | 27/03/2023 | 27/03/2024 | A. G. ENTERPRISE | 93.34 | 0 | 0 | 50
4 | BIRBHUM | Rampurhat-II | Birbhum Division | Sahapur Piped water Supply Scheme. | SM/13649 | New | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 219/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 5.24 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Sahapur Piped water Supply Scheme. | SM/13649 | New | Quotation for new service connection at Sahapur TW No-I (Block-Rampurhat-II) |  |  | BILL/02222/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.89 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Sahapur Piped water Supply Scheme. | SM/13649 | New | WBSEDCL QUOTATION FOR SAHAPUR TW-II |  |  | BILL/02248/2023-2024 |  | 14/03/2024 | 14/03/2024 | WBSEDCL | 3.21 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Birbhum Division | Sahapur Piped water Supply Scheme. | SM/13649 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 09/11/2025 | SUNIL RABI DAS | 1157.77 | 163.54 | 14.13 | 40
Total | [13 empty] | 1495.8 | 163.54 | 10.93