## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sekupur piped water supply scheme. | SM/13650 | New | Providing Electro-mechanical accessories and others for Sekupur PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000436/2023-2024 | 2108/BOL.MD. | 22/08/2023 | 21/10/2023 | QUAZI NOZRUL ISLAM | 28 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Sekupur piped water supply scheme. | SM/13650 | New | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 1403/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 9.14 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Sekupur piped water supply scheme. | SM/13650 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 2449/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 4.69 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Sekupur piped water supply scheme. | SM/13650 | New | Sinking of 150 mm. X 100 mm Dia deep tubewell , construction of 100 CuM capacity O.H.R.with soil Investigation, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main, Laying distribution with FHTC and different works related to SEKUPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE,JE1,JE3 | ORD/000104/2024-2025 | 2111/BHM | 29/07/2024 | 29/07/2025 | MAMATA USHA ENTERPRISE | 243.97 | 0 | 0 | 20
Total | [13 empty] | 285.8 | 0 | 0