## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Continuation Work Order for Preparation & Submission of DPR for (Shaspur) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000623/2022-2023 | 204/RSD | 13/06/2022 | 28/07/2022 | ECO CARE | 4.73 | 4.71 | 99.66 | 100
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 1555/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 94.6 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Birbhum Division | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 220/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 4 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Quotation for new service connection at Shaspur TW No-II (Block-Rampurhat-II) |  |  | BILL/02225/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.87 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | WBSEDCL QUOTATION FOR SHASPUR TW-II |  |  | BILL/02250/2023-2024 | BP-2023-24-310 | 18/03/2024 | 18/03/2024 | WBSEDCL | 2.87 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | WBSEDCL QUOTATION FOR SHASPUR TW-1 |  |  | BILL/02241/2023-2024 | BP-2023-24-309 | 18/03/2024 | 18/03/2024 | WBSEDCL | 2.73 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Quotation for new service connection at Shaspur TW No-I (Block-Rampurhat-II) |  |  | BILL/02193/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.73 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-II | Birbhum Division | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 09/11/2025 | SUNIL RABI DAS | 1157.77 | 185.67 | 16.04 | 40
9 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Providing Electro-mechanical accessories and others for Shaspur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000483/2023-2024 | 2234/Bol.MD | 12/09/2023 | 01/07/2025 | SINHA ELECTRICALS | 45.39 | 19.75 | 43.5 | 90
10 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Supply & delivery of UPVC Column pipes at store for Sahapur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000520/2024-2025 | 1452./AE-III | 09/09/2024 | 01/01/2025 | S.B ENTERPRISE | 2.69 | 2.69 | 100 | 100
11 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. | SM/13651 | New | Supply delivery and fitting fixing of Yard Lighting Luminaries accessories for Shaspur water supply scheme Block Rampurhat II under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000607/2024-2025 | 1460./AE-III | 09/09/2024 | 24/09/2024 | GOENKA ENTERPRISE | 2.67 | 0 | 0 | 100
Total | [13 empty] | 1323.06 | 212.81 | 16.08