## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | Srikantapur piped water supply scheme. | SM/13652 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 1578/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 26.45 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | Srikantapur piped water supply scheme. | SM/13652 | New | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 2448/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 13.19 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Srikantapur piped water supply scheme. | SM/13652 | New | Providing Electro-mechanical accessories and others for SRIKANTAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000583/2023-2024 | 3387/Bol.MD | 16/10/2023 | 15/12/2023 | SARKAR ELECTRICAL | 28.28 | 15.46 | 54.68 | 20
4 | BIRBHUM | Mohammad Bazar | Birbhum Division | Srikantapur piped water supply scheme. | SM/13652 | New | Sinking of 3 nos. 200mm X 165mm dia x 300 mtr. deep Tube Well by Rig boring method including connecting pipeline and all other allied works under Srikantapur Piped Water Supply Scheme under Birbhum Division, P.H.E. Dte. (2nd Call) | AE(HQ) | JE1 | ORD/000577/2024-2025 | 437/BHM | 10/02/2025 | 11/04/2025 | M/S R B ENTERPRISE | 20.14 | 0 | 0 | 0
5 | BIRBHUM | Mohammad Bazar | Birbhum Division | Srikantapur piped water supply scheme. | SM/13652 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 300 CuM capacity O.H.R. Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to SRIKANTAPUR water supply scheme at & its adjoining mouzas water supply scheme within Md. Bazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE(HQ) | Estimator,JE1 | ORD/000103/2024-2025 | 2112/BHM | 29/07/2024 | 30/06/2026 | M/S R B ENTERPRISE | 571.1 | 0 | 0 | 0
Total | [13 empty] | 659.16 | 15.46 | 2.35