## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | New | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 1575/BHM | 26/04/2023 |  | Resource Division | 15.86 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ULANDI Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte" | AE | JE1 | ORD/000643/2022-2023 | 154/BSD | 18/04/2022 | 17/07/2022 | M/S R DUTTA & CO. | 3.93 | 1.76 | 44.65 | 100
3 | BIRBHUM | Illambazar | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | New | Construction of 150 CUM capacity OHR including Soil Investigation, 5.09 m X 4.1 m Pump House/Chlorine Room with Sanitary, Laying of Rising Main and Distribution System and FHTC and Construction of Boundary Wall Approach Road and Land Development works at H/W site and 2 nd T/W site under Ulandi PIPED WATER SUPPLY SCHEME within Illambazar Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE3 | ORD/000092/2024-2025 | 2037/BHM | 19/07/2024 | 19/07/2025 | SHIBU BISWAS, BADARTALA , BASIRHAT, PIN - 743292 | 413.14 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Central Drilling | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Illambazar | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME | SM/13654 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 2381/BHM | 27/08/2024 |  | Resource Division | 9.66 | 0 | 0 | 0
Total | [13 empty] | 21782.35 | 1.76 | 0.01