## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 1357/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 13.87 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | AE | JE4 | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 01/01/2026 | AMAL DUTTA ROY | 1648.21 | 0 | 0 | 12
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | New | NEW SERVICE CONNECTION AT BIDYADHARPUR T/W- II PIPED WATER SUPPLY SCHEME. |  |  | BILL/01157/2024-2025 | BP-24-25-312 | 22/01/2025 | 22/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.54 | 0 | 0 | 0
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | New | NEW SERVICE CONNECTION AT BIDYADHARPUR T/W- I PIPED WATER SUPPLY SCHEME. |  |  | BILL/01158/2024-2025 | BP-24-25-313 | 22/01/2025 | 22/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0 | 0
5 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Bidhyadharpur Piped Water Supply Scheme. | SM/13708 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 34.37 | 0.16 | 11
Total | [13 empty] | 23011.43 | 34.37 | 0.15