## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1493/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 17.09 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Providing Electro-mechanical accessories and others for Chhamna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000844/2023-2024 | 3283/BOL.MD | 29/09/2023 | 28/11/2023 | SUNIL RABIDAS | 55.68 | 0 | 0 | 40
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS, Block: Mayureswar- II (Pump House No. I), under Bolpur MechanicalDivision, P.H.E Dte. | Assistant Engineer-III | Junior Engineer | ORD/000836/2024-2025 | 1636./AE-III | 21/10/2024 | 21/01/2025 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Chamna PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001216/2023-2024 | 401/Bol.MD | 07/03/2024 | 21/04/2024 | M/S SWAPAN BANERJEE | 25.28 | 0 | 0 | 90
5 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS,Block: Mayureswar- II (Pump House No. II), under Bolpur MechanicalDivision, P.H.E Dte. |  |  | ORD/000837/2024-2025 | 1637./AE-III | 21/10/2024 | 21/01/2025 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000834/2022-2023 | 287/RSD | 31/08/2022 | 15/10/2022 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 0 | 100
7 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000835/2022-2023 | 371/RSD | 21/09/2022 | 05/11/2022 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
8 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 233/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 8.62 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION, PHE Dte... |  |  | BILL/00024/2024-2025 | BP-24-25-11 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.1 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | New service connection at Chhamna Pump House-3, under Bolpur Mech. Division, P.H.e. Dte. |  |  | BILL/00074/2024-2025 | BP-2024-2025-28 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
11 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-II UNDER BOLPUR MECHANICAL DIVISION PHE Dte... |  |  | BILL/00023/2024-2025 | BP-24-25-10 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | 0
Total | [13 empty] | 127.03 | 0 | 0