## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1493/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 17.09 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Providing Electro-mechanical accessories and others for Chhamna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000844/2023-2024 | 3283/BOL.MD | 29/09/2023 | 28/11/2023 | SUNIL RABIDAS | 55.68 | 26.15 | 46.96 | 40
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS, Block: Mayureswar- II (Pump House No. I), under Bolpur MechanicalDivision, P.H.E Dte. | Assistant Engineer-III | Junior Engineer | ORD/000836/2024-2025 | 1636./AE-III | 21/10/2024 | 21/01/2025 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Chamna PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001216/2023-2024 | 401/Bol.MD | 07/03/2024 | 21/04/2024 | M/S SWAPAN BANERJEE | 25.28 | 23.76 | 93.97 | 90
5 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS,Block: Mayureswar- II (Pump House No. II), under Bolpur MechanicalDivision, P.H.E Dte. |  |  | ORD/000837/2024-2025 | 1637./AE-III | 21/10/2024 | 21/01/2025 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000834/2022-2023 | 287/RSD | 31/08/2022 | 15/10/2022 | ENVIROTECH SOLUTIONS | 3.43 | 2.7 | 78.6 | 100
7 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000835/2022-2023 | 371/RSD | 21/09/2022 | 05/11/2022 | ENVIROTECH SOLUTIONS | 2.5 | 2.38 | 94.95 | 100
8 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 233/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 8.62 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION, PHE Dte... |  |  | BILL/00024/2024-2025 | BP-24-25-11 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.1 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | New service connection at Chhamna Pump House-3, under Bolpur Mech. Division, P.H.e. Dte. |  |  | BILL/00074/2024-2025 | BP-2024-2025-28 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
11 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-II UNDER BOLPUR MECHANICAL DIVISION PHE Dte... |  |  | BILL/00023/2024-2025 | BP-24-25-10 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | 0
12 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Different works related to Water Supply Scheme at CHHAMNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000190/2023-2024 | 3020/BHM | 14/07/2023 | 01/07/2025 | S K CONSTRUCTION | 557.28 | 393.44 | 70.6 | 40
13 | BIRBHUM | Mayureswar-II | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/13710 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 752.15 | 448.41 | 59.62