## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | Gaytha Piped Water Supply Scheme | SM/13712 | New | Different works related to water supply scheme at GAYTHA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE | JE3 | ORD/000066/2023-2024 | 1311/BHM | 19/04/2023 | 14/01/2024 | RAJ ASSOCIATES | 226.66 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - II | Birbhum Division | Gaytha Piped Water Supply Scheme | SM/13712 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 1544/BHM | 26/04/2023 |  | Resource Division | 13.99 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat - II | Birbhum Division | Gaytha Piped Water Supply Scheme | SM/13712 | New | Continuation Work Order for Preparation & Submission of DPR for (Gaytha) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000630/2022-2023 | 229/RSD | 24/06/2022 | 08/08/2022 | ECO CARE | 3.63 | 3.19 | 87.65 | 100
4 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | wbsedcl quotation money for gaytha p.h.no.1 pwss |  |  | BILL/01431/2023-2024 | BP-23-24-152 | 04/12/2023 |  | WBSEDCL | 2.74 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | wbsedcl quotation money for gaytha p.h.no.1 pwss |  |  | BILL/01431/2023-2024 | BP-23-24-152 | 04/12/2023 |  | WBSEDCL | 2.74 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | wbsedcl quotation money for gaytha p.h.no.2 pwss |  |  | BILL/01432/2023-2024 | BP-23-24-151 | 04/12/2023 |  | WBSEDCL | 2.36 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000480/2023-2024 | 2232/Bol.MD | 12/09/2023 | 11/11/2023 | WEST BENGAL ENGINEERING CO. | 44.34 | 8.81 | 19.86 | 40
8 | BIRBHUM | Rampurhat - II | Birbhum Division | Gaytha Piped Water Supply Scheme | SM/13712 | New | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 224/BHM | 24/01/2024 |  | Resource Division | 4 | 0 | 0 | 0
9 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. |  |  | ORD/000001/2024-2025 | 684./AE-III | 08/04/2024 | 22/04/2024 | WEST BENGAL ENGINEERING CO. | 1.58 | 0 | 0 | 0
10 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Gaytha Piped Water Supply Scheme | SM/13712 | New | Supply & delivery of 16 mm² x 3 core Al.Ar. Cable of Gaytha water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. " | Assistant Engineer-III | Junior Engineer | ORD/000459/2024-2025 | 1307./AE-III | 28/08/2024 | 04/09/2024 | SINHA ELECTRICALS | 4.87 | 3.85 | 79.05 | 0
Total | [13 empty] | 306.93 | 15.84 | 5.16