## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kasba Piped Water Supply Scheme. | SM/13713 | New | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 1359/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 13.67 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Kasba Piped Water Supply Scheme. | SM/13713 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 28.61 | 0.13 | 11
3 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kasba Piped Water Supply Scheme. | SM/13713 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 31/12/2025 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 24.17 | 0.9 | 60
4 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kasba Piped Water Supply Scheme. | SM/13713 | New | Continuation order against "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE. Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2024 to 31.03.2025. | Assistant Engineer | JE3 | ORD/000313/2024-2025 | 873/BSD | 27/09/2024 | 28/03/2025 | SK AKRAM HOSSAIN | 0.86 | 2.37 | 277.28 | 0
Total | [13 empty] | 24039.27 | 55.15 | 0.23