## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | Podda Piped Water Supply Scheme | SM/13714 | New | Preparation & Submission of DPR for (Podda) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000557/2022-2023 | 171/RSD | 29/04/2022 | 13/06/2022 | ECO CARE | 2.91 | 2.53 | 87.01 | 100
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Podda Piped Water Supply Scheme | SM/13714 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 1542/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 12.98 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Podda Piped Water Supply Scheme | SM/13714 | New | Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000354/2023-2024 | 1749/Bol.MD | 27/07/2023 | 25/09/2023 | S.K.ELECTRICALS | 44.24 | 39.99 | 90.4 | 90
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Podda Piped Water Supply Scheme | SM/13714 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Podda PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001256/2023-2024 | 528/BOL.MD | 14/03/2024 | 13/05/2024 | M/S. S.G ENTERPRISE | 7.62 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Birbhum Division | Podda Piped Water Supply Scheme | SM/13714 | New | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 222/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 3.26 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Podda Piped Water Supply Scheme | SM/13714 | New | wbsedcl quotation money for poddsa p.h.no.1 pwss |  |  | BILL/01434/2023-2024 | BP-23-24-154 | 04/12/2023 | 04/12/2023 | WBSEDCL | 4.8 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Podda Piped Water Supply Scheme | SM/13714 | New | wbsedcl quotation money for podda pwss |  |  | BILL/01433/2023-2024 | BP-23-24-153 | 04/12/2023 | 04/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-II | Birbhum Division | Podda Piped Water Supply Scheme | SM/13714 | New | Different works related to water supply scheme at PODDA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE | JE2,JE3 | ORD/000065/2023-2024 | 1310/BHM | 19/04/2023 | 17/12/2025 | P. C. CONSTRUCTION | 210.99 | 78.79 | 37.34 | 80
9 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Podda Piped Water Supply Scheme | SM/13714 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000007/2024-2025 | 687/AE-III | 08/04/2024 | 22/04/2024 | S.K.ELECTRICALS | 1.58 | 0 | 0 | 100
Total | [13 empty] | 291.28 | 121.32 | 41.65