## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 1539/BHM | 26/04/2023 |  | Resource Division | 56.84 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | Providing Electro-mechanical accessories and others for Purba Anantapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000479/2023-2024 | 2231/Bol.MD | 12/09/2023 | 11/11/2023 | ORIENTAL ENGINEERING CO. | 44.37 | 6.78 | 15.28 | 40
3 | BIRBHUM | Rampurhat - II | Birbhum Division | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | Continuation Work Order for Preparation & Submission of DPR for (Purba Anantapur) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000632/2022-2023 | 235/RSD | 04/07/2022 | 18/08/2022 | ECO CARE | 3.63 | 1.74 | 47.91 | 100
4 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | WBSEDCL QUOTATION FOR PURBA ANANTAPUR WS SCHEME UNDER BOL MD |  |  | BILL/01554/2023-2024 | BP-23-24-200 | 28/12/2023 |  | WBSEDCL | 3.81 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - II | Birbhum Division | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | Material Requisition To Resource Division |  |  | RTOR000221/2023-2024 | 223/BHM | 24/01/2024 |  | Resource Division | 4.31 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | WBSEDCL QUOTATION FOR PURBA ANANTAPUR W S P H NO I WS SCHEME |  |  | BILL/01779/2023-2024 | BP-23-24-255 | 06/02/2024 |  | WBSEDCL | 5.65 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | WBSEDCL QUOTATION FOR PURBA ANANTAPUR W S P H NO I WS SCHEME |  |  | BILL/01779/2023-2024 | BP-23-24-255 | 06/02/2024 |  | WBSEDCL | 5.65 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat - II | Birbhum Division | Purba Anantapur Piped Water Supply Scheme | SM/13715 | New | Different works related to water supply scheme at PURBA ANANTAPUR & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000030/2023-2024 | 1193/BHM | 12/04/2023 | 30/06/2024 | MEHEBUB RAHAMAN | 257.78 | 67.29 | 26.1 | 50
Total | [13 empty] | 382.04 | 75.81 | 19.84