## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHEPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/000640/2022-2023 | 144/BSD | 12/04/2022 | 11/07/2022 | RADIANT | 4.36 | 0 | 0 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 2178/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 8.91 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 2450/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 9.25 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Central Drilling | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Nanoor | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Construction of 200 CuM.capacity OHR with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying Rising Main,Distribution System with FHTC and different works related to BHEPUR PIPED WATER SUPPLY SCHEME (TSM/015433) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE2 ,JE4 | ORD/000105/2024-2025 | 2109/BHM | 29/07/2024 | 29/07/2026 | MAMATA USHA ENTERPRISE | 382.93 | 0 | 0 | 35
6 | BIRBHUM | Nanoor | Bolpur Mechanical | BHEPUR PIPED WATER SUPPLY SCHEME | SM/13759 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhepur WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000959/2024-2025 | 4528/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 60
Total | [13 empty] | 21820.3 | 0 | 0