## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for PANCHPARA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000658/2022-2023 | 179/BSD | 05/05/2022 | 01/11/2022 | APEX ENGINEERING | 3.87 | 3.19 | 82.42 | 100
2 | BIRBHUM | Labpur | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2395/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 11.4 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,JE1,JE3 | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 04/07/2026 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
4 | BIRBHUM | Labpur | Bolpur Mechanical | PANCHPARA PIPED WATER SUPPLY SCHEME | SM/13951 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Panchpara PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001132/2024-2025 | 333/BOL.MD | 19/02/2025 | 17/10/2025 | PADMA ENGINEERING CO. | 75.59 | 0 | 0 | 50
Total | [13 empty] | 2105.59 | 3.19 | 0.15