## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1535/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 14.49 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ANGORA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte". (PART - A) | AE | JE4 | ORD/000730/2022-2023 | 215/BSD | 31/05/2022 | 27/11/2022 | RADIANT | 4.94 | 4.89 | 98.95 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Material Requisition To Resource Division |  |  | RTOR000053/2024-2025 | 3266/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 11.22 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Different works related to water supply scheme at ANGORA PIPED WATER SUPPLY SCHEME (TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000149/2024-2025 | 2599/BHM | 10/09/2024 | 10/09/2025 | CHIRANJIB DAS | 419.76 | 0 | 0 | 25
5 | BIRBHUM | Nanoor | Bolpur Mechanical | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Angora & Charkalgram Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000968/2024-2025 | 4537/BOL.MD | 20/12/2024 | 01/10/2025 | MENAKA ENTERPRISE | 73.34 | 14.77 | 20.13 | 100
6 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
7 | BIRBHUM | Nanoor | Central Drilling | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21903.81 | 19.66 | 0.09