## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1535/BHM | 26/04/2023 |  | Resource Division | 14.49 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ANGORA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte". (PART - A) | AE | JE4 | ORD/000730/2022-2023 | 215/BSD | 31/05/2022 | 27/11/2022 | RADIANT | 4.94 | 2.45 | 49.47 | 100
3 | BIRBHUM | Nanoor | Central Drilling | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | BIRBHUM | Nanoor | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME | SM/13971 | New | Different works related to water supply scheme at ANGORA PIPED WATER SUPPLY SCHEME (TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000149/2024-2025 | 2599/BHM | 10/09/2024 | 10/09/2025 | CHIRANJIB DAS | 419.76 | 0 | 0 | 0
Total | [13 empty] | 21778.96 | 2.45 | 0.01