## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Sandhyajol Piped Water Supply Scheme | SM/13981 | New | Providing Electro-mechanical accessories and others for Sandhyajol PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000475/2023-2024 | 2228/Bol.MD | 12/09/2023 | 11/11/2023 | P. K. ENGINEERING | 44.41 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Sandhyajol Piped Water Supply Scheme | SM/13981 | New | Continuation Work Order for Preparation & Submission of DPR for (Sandhyajol) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000634/2022-2023 | 241/RSD | 13/07/2022 | 27/08/2022 | ECO CARE | 4.73 | 0 | 0 | 100
3 | BIRBHUM | Rampurhat-II | Birbhum Division | Sandhyajol Piped Water Supply Scheme | SM/13981 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1568/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 45.61 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-II | Birbhum Division | Sandhyajol Piped Water Supply Scheme | SM/13981 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 2492/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 12.42 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Birbhum Division | Sandhyajol Piped Water Supply Scheme | SM/13981 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at SANDHYAJOL & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2,JE3 | ORD/000124/2024-2025 | 2224/BHM | 12/08/2024 | 12/08/2026 | SUNIL RABI DAS | 386.48 | 0 | 0 | 20
Total | [13 empty] | 493.64 | 0 | 0