## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | New | Continuation Work Order for Preparation & Submission of DPR for (Satpalsa) Water Supply Scheme under Mayureswar-II Development Block. | AE | JE3 | ORD/000625/2022-2023 | 211/RSD | 16/06/2022 | 31/07/2022 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 0 | 100
2 | BIRBHUM | Mayureswar-II | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1454/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 17.5 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | New | Providing Electro-mechanical accessories and others for Satpalsa PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000838/2023-2024 | 3277/Bol.MD | 29/09/2023 | 28/11/2023 | GHOSH ENGINEERING SYNDICATE | 44.05 | 0 | 0 | 40
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | New | Material Requisition To Resource Division |  |  | RTOR000214/2023-2024 | 232/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 5.5 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | SM/13982 | New | Different works related to Water Supply Scheme at SATPALSA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000399/2023-2024 | 4135/BHM | 18/10/2023 | 04/01/2026 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 394.79 | 0 | 0 | 35
Total | [13 empty] | 466.12 | 0 | 0