## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1532/BHM | 26/04/2023 |  | Resource Division | 6.01 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | WBSEDCL QUOTATION BILL FOR BAJITPUR WS SCHEME |  |  | BILL/01152/2023-2024 | BP-23-24-94 | 26/09/2023 |  | WBSEDCL | 2.93 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar - I | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Continuation Work Order for Preparation & Submission of DPR for (Bajitpur) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000563/2022-2023 | 185/RSD | 06/05/2022 | 04/08/2022 | ENVIROTECH SOLUTIONS | 2.86 | 1.3 | 45.54 | 100
4 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Providing Electro-mechanical accessories and others for Bajitpur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000350/2023-2024 | 1747/Bol.MD | 27/07/2023 | 25/09/2023 | MAHADEV ENTERPRISE | 43.79 | 8.6 | 19.64 | 30
5 | BIRBHUM | Mayureswar - I | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 197/BHM | 22/01/2024 |  | Resource Division | 2.18 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | WBSEDCL QUOTATION FOR RBAJITPUR ws scheme |  |  | BILL/01843/2023-2024 | BP-23-24-264 | 07/02/2024 |  | WBSEDCL | 1.7 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | WBSEDCL QUOTATION FOR RBAJITPUR ws scheme |  |  | BILL/01843/2023-2024 | BP-23-24-264 | 07/02/2024 |  | WBSEDCL | 1.7 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar - I | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Different works related to water supply scheme at BAJITPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (SL NO 05) | AE | JE1 | ORD/000525/2022-2023 | 618/BHM | 27/02/2023 | 24/11/2023 | S.D CONSTRUCTION | 278.84 | 82.86 | 29.72 | 60
9 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Supply and Delivery of Pumping Machinery for Bajitpur Water Supply Scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001324/2023-2024 | 615/AE-III | 27/03/2024 | 03/04/2024 | MAHADEV ENTERPRISE | 1.49 | 0.95 | 64 | 100
10 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Supply & delivery of Chlorinat0r at Bajitpur Piped Water Supply Scheme under Bolpur Mechanical Division ,P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000369/2024-2025 | 1192./AE-III | 12/08/2024 | 22/08/2024 | R.K.ENTERPRISE | 0.9 | 0 | 0 | 0
11 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13983 | New | Supply & delivery of UPVC Column pipes at store for Bajitpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000445/2024-2025 | 1298./AE-III | 27/08/2024 | 03/09/2024 | MS SM ELECTRICAL | 1.9 | 0 | 0 | 0
Total | [13 empty] | 344.3 | 93.72 | 27.22