## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | WBSEDCL QUOATATION FOR kHENDAMARA WS SCHEME |  |  | BILL/00642/2023-2024 | BP-2023-2024-54 | 17/07/2023 |  | WBSEDCL | 3.39 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - I | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Sinking of 02 Nos Tube wells 200 mm dia depth 36.0 mm each depth, fitted with PVC pipe and fiber glass Strainer at Salbani River bank for Khadamara PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000360/2022-2023 | 448/RSD | 08/12/2022 | 07/01/2023 | ANKITA CHAKRABORTY | 4.68 | 0 | 0 | 100
3 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | WBSEDCL QUOTATION FOR UTTAR BAKHEDAMARA WS SCHEME |  |  | BILL/01475/2023-2024 | BP-23-24-196 | 14/12/2023 |  | WBSEDCL | 1.96 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | WBSEDCL QUOTATION FOR UTTAR BAKHEDAMARA WS SCHEME |  |  | BILL/01475/2023-2024 | BP-23-24-196 | 14/12/2023 |  | WBSEDCL | 1.96 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Providing and Installation of Submersible pumping machinaries at newly sunk Tube Wells and allied works at Khedamara PWSS Block-Rampurhat-I under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/000306/2023-2024 | 1501/Bol.MD | 17/07/2023 | 15/09/2023 | MUKHERJEE ART CENTRE | 19.28 | 11.3 | 58.63 | 80
6 | BIRBHUM | Rampurhat - I | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Sinking of Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia including connecting main for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District under Rampurhat Sub-Division, Birbhum Division, P.H.E Dte | AE | JE1 | ORD/000137/2023-2024 | 2268/BHM | 13/07/2023 | 12/08/2023 | JAYANTA BARAL | 4.53 | 1.36 | 30.06 | 100
7 | BIRBHUM | Rampurhat - I | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Construction of Switch Room size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement For Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat Sub-Division, P.H.E. Dte. | AE | JE1 | ORD/000359/2022-2023 | 447/RSD | 08/12/2022 | 22/01/2023 | SUBHRANIL DAS | 4.98 | 4.82 | 96.7 | 0
8 | BIRBHUM | Rampurhat - I | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Sinking of 01 nos. additional Tubewell, 200mm dia all through 120 mt. deep tubewell with Rising Main along with Construction of Switch Room 3.60 m X 3.0 m with Sanitary arrangement and balance FHTC for Khedamara PWSS under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000668/2023-2024 | 1028/BHM | 15/03/2024 | 29/04/2024 | M/S MD AMINUL ISLAM | 40.81 | 0 | 0 | 0
9 | BIRBHUM | Rampurhat - I | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | SM/14016 | New | Laying of Rising Main , Distribution system and Providing FHTC including all allied Works for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat - I Block within Birbhum District. (Sl. No.8) | AE | JE1,JE3 | ORD/000353/2022-2023 | 2689/BHM | 06/12/2022 | 04/02/2023 | M/S MD AMINUL ISLAM | 98.43 | 65.77 | 66.82 | 90
Total | [13 empty] | 180.02 | 83.26 | 46.25