## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 3283/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 0.51 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Rajpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001258/2023-2024 | 531/BOL.MD | 14/03/2024 | 13/05/2024 | NITESH MANAGEMENT | 7.58 | 0 | 0 | 60
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Supply & delivery of Al.Ar cable for Rajpur Piped water supply scheme under Bolpur Mechanical Division(Block-Rajnagar), PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000556/2024-2025 | 1477./AE-III | 11/09/2024 | 18/09/2024 | M. S. ENTERPRISE | 4.31 | 0 | 0 | 100
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | QUOTATION FOR RAJPUR PWSS AT RAJNAGAR BLOCK |  |  | BILL/00010/2024-2025 | BP-24-25-08 | 09/04/2024 | 09/04/2024 | WBSEDCL | 9.47 | 0 | 0 | 0
5 | BIRBHUM | Rajnagar | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | New | Different works related to water supply scheme at RAJPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000072/2023-2024 | 1346/BHM | 20/04/2023 | 24/06/2025 | MUSKAN ENTERPRISE | 410.62 | 0 | 0 | 25
6 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Providing Electro-mechanical accessories and others for Rajpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000906/2023-2024 | 3550/Bol.MD | 01/12/2023 | 08/09/2025 | GLACIER ENGINEERING CO. | 87.05 | 0 | 0 | 89
7 | BIRBHUM | Rajnagar | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 587.38 | 0 | 0