## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 3283/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 0.51 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Rajpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001258/2023-2024 | 531/BOL.MD | 14/03/2024 | 13/05/2024 | NITESH MANAGEMENT | 7.58 | 0 | 0 | 60
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Supply & delivery of Al.Ar cable for Rajpur Piped water supply scheme under Bolpur Mechanical Division(Block-Rajnagar), PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000556/2024-2025 | 1477./AE-III | 11/09/2024 | 18/09/2024 | M. S. ENTERPRISE | 4.31 | 0 | 0 | 100
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | QUOTATION FOR RAJPUR PWSS AT RAJNAGAR BLOCK |  |  | BILL/00010/2024-2025 | BP-24-25-08 | 09/04/2024 | 09/04/2024 | WBSEDCL | 9.47 | 0 | 0 | 0
5 | BIRBHUM | Rajnagar | Birbhum Division | Rajpur Piped Water Supply Scheme | SM/14026 | New | Different works related to water supply scheme at RAJPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000072/2023-2024 | 1346/BHM | 20/04/2023 | 24/06/2025 | MUSKAN ENTERPRISE | 410.62 | 0 | 0 | 25
6 | BIRBHUM | Rajnagar | Bolpur Mechanical | Rajpur Piped Water Supply Scheme | SM/14026 | New | Providing Electro-mechanical accessories and others for Rajpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000906/2023-2024 | 3550/Bol.MD | 01/12/2023 | 08/09/2025 | GLACIER ENGINEERING CO. | 87.05 | 0 | 0 | 89
Total | [13 empty] | 519.54 | 0 | 0