## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - I | Birbhum Division | Radipur Piped Water Supply Scheme. | SM/14027 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 1576/BHM | 26/04/2023 |  | Resource Division | 13.07 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Radipur Piped Water Supply Scheme. | SM/14027 | New | Providing Electro-mechanical accessories and others for Radipur & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000928/2023-2024 | 3528/Bol.MD | 29/11/2023 | 28/01/2024 | ASHIM UDYOG | 27.61 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat - I | Birbhum Division | Radipur Piped Water Supply Scheme. | SM/14027 | New | Sinking of 250 mm.X 150 mm.Dia Tube Well (2 nos) Drilling by Direct Rotary method ,Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Radipur & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division,PHE Dte | AE | JE3 | ORD/000156/2024-2025 | 2644/BHM | 12/09/2024 | 12/09/2025 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD | 379.68 | 0 | 0 | 0
Total | [13 empty] | 420.36 | 0 | 0