## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar,Nalhati-I | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. | SM/14028 | New | Supply and delivery of Column pipe and other at Haridaspur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000412/2023-2024 | 950/AE-III | 04/07/2023 | 11/07/2023 | J.K.ENGINEERING CO | 0.97 | 0 | 0 | 100
2 | BIRBHUM | Mohammad Bazar,Nalhati-I | Birbhum Division | Haridaspur Piped Water Supply Scheme. | SM/14028 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 1623/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 42.21 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar,Nalhati-I | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. | SM/14028 | New | Providing Electro-mechanical accessories and others for HARIDASPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000292/2023-2024 | 1498/Bol.MD | 17/07/2023 | 15/09/2023 | C M ENTERPRISE | 41.17 | 0 | 0 | 40
4 | BIRBHUM | Mohammad Bazar,Nalhati-I | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. | SM/14028 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Haridaspur PWSS under Md. Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Driller in Charge | Junior Engineer | ORD/001246/2023-2024 | 523/BOL.MD | 14/03/2024 | 13/05/2024 | S. K. ENTERPRISE | 7.6 | 0 | 0 | 100
5 | BIRBHUM | Mohammad Bazar,Nalhati-I | Birbhum Division | Haridaspur Piped Water Supply Scheme. | SM/14028 | New | Different works related to water supply scheme at HARIDASPUR & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE(HQ) | JE | ORD/000361/2023-2024 | 3974/BHM | 04/10/2023 | 04/07/2024 | M/S R B ENTERPRISE | 738.23 | 0 | 0 | 20
Total | [13 empty] | 830.17 | 0 | 0