## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Banhat Piped Water Supply Scheme. | SM/14029 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 1592/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 18.13 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Birbhum Division | Banhat Piped Water Supply Scheme. | SM/14029 | New | Different works related to water supply scheme at BANHAT & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000571/2022-2023 | 904/BHM | 22/03/2023 | 02/02/2025 | PRALAY ROY | 331.4 | 244.5 | 73.78 | 38
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Banhat Piped Water Supply Scheme. | SM/14029 | New | Material Requisition To Resource Division |  |  | RTOR000216/2023-2024 | 230/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 0.12 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Banhat Piped Water Supply Scheme. | SM/14029 | New | WBSEDCL QUOTATION FOR BONHAT W S P H NO I WS SCHEME |  |  | BILL/01782/2023-2024 | BP-23-24-249 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Banhat Piped Water Supply Scheme. | SM/14029 | New | QUOTATION FOR BANHAT PH-II RAMPURHAT-I BLOCK |  |  | BILL/00008/2024-2025 | BP-24-25-06 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.23 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Banhat Piped Water Supply Scheme. | SM/14029 | New | Providing Electro-mechanical accessories and others for Banhat & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000355/2023-2024 | 1750/Bol.MD | 27/07/2023 | 01/04/2025 | PADMA ENGINEERING CO. | 27.7 | 17.44 | 62.94 | 100
7 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Banhat Piped Water Supply Scheme. | SM/14029 | New | Laying of power cable of Submersible Pumpining Machinery at newly yield Tube Well and other allied works at Bonhat Piped Water Supply Scheme PH-I , Block-Rampurhat-I under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/001089/2024-2025 | 236./AE-III | 29/01/2025 | 01/04/2025 | PADMA ENGINEERING CO. | 2.08 | 0 | 0 | 100
8 | BIRBHUM | Rampurhat-I | Birbhum Division | Banhat Piped Water Supply Scheme. | SM/14029 | New | DI Connecting Line & R.C.C Pipe Carring Structure over Irrigation Canal near Head Work Site Under BANHAT Water Supply Scheme Within Rampurhat Sub-Division Birbhum Division PHE Dte. | AE | JE3 | ORD/000132/2025-2026 | 669/RSD | 24/07/2025 | 22/10/2025 | PULAK KUMAR PAL | 4.64 | 0 | 0 | 100
Total | [13 empty] | 390.84 | 261.94 | 67.02