## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Bolpur Mechanical | Chormara Piped Water Supply Scheme. | SM/14030 | New | Providing Electro-mechanical accessories and others for Chormara PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000426/2023-2024 | 2103/BOL.MD. | 22/08/2023 | 21/10/2023 | RMD TRADING | 27.44 | 0 | 0 | 0
2 | BIRBHUM | Suri-I | Birbhum Division | Chormara Piped Water Supply Scheme. | SM/14030 | New | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 1380/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 13.47 | 0 | 0 | 0
3 | BIRBHUM | Suri-I | Bolpur Mechanical | Chormara Piped Water Supply Scheme. | SM/14030 | New | Lowering of 5HP Submersible Pumpining Machinery at nwely yield Tube Well and other allied works at Purba Bankathi water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000838/2024-2025 | 1675./AE-III | 24/10/2024 | 14/11/2024 | SATYAJIT GHOSH | 2.67 | 0 | 0 | 100
4 | BIRBHUM | Suri-I | Birbhum Division | Chormara Piped Water Supply Scheme. | SM/14030 | New | Different works for CHORMARA & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000113/2023-2024 | 1878/BHM | 31/05/2023 | 02/08/2025 | SPIRIT ENGINEERS CO OP SOCIETY LTD | 307.6 | 0 | 0 | 15
Total | [13 empty] | 351.17 | 0 | 0