## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1586/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 111.93 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Providing Electro-mechanical accessories and others for Shankarpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000907/2023-2024 | 3551/Bol.MD | 01/12/2023 | 29/02/2024 | QUAZI NOZRUL ISLAM | 85.3 | 15.4 | 18.06 | 20
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001238/2023-2024 | 536/BOL.MD | 14/03/2024 | 13/05/2024 | DEY ENTERPRISE | 5.77 | 0 | 0 | 0
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,PHEDte | Assistant Engineer-III | Junior Engineer | ORD/001239/2023-2024 | 535/BOL.MD | 14/03/2024 | 13/05/2024 | TULIP ENTERPRISE | 5.41 | 4.96 | 91.58 | 30
5 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | WBSEDCL QUOTATION FOR SHANKARPUR WATER SUPPLY SCHEME |  |  | BILL/01832/2023-2024 | BP-23-24-259 | 06/02/2024 | 06/02/2024 | WBSEDCL | 21.4 | 0 | 0 | 0
6 | BIRBHUM | Rajnagar | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | New | Different works related to water supply scheme at SHANKARPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte.150 | AE | JE1 | ORD/000021/2023-2024 | 1094/BHM | 06/04/2023 | 01/10/2025 | SYED GOLAM ZILANI | 353.43 | 112.45 | 31.82 | 30
Total | [13 empty] | 583.24 | 132.81 | 22.77