## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1586/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 111.93 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Providing Electro-mechanical accessories and others for Shankarpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000907/2023-2024 | 3551/Bol.MD | 01/12/2023 | 29/02/2024 | QUAZI NOZRUL ISLAM | 85.3 | 0 | 0 | 20
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001238/2023-2024 | 536/BOL.MD | 14/03/2024 | 13/05/2024 | DEY ENTERPRISE | 5.77 | 0 | 0 | 0
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,PHEDte | Assistant Engineer-III | Junior Engineer | ORD/001239/2023-2024 | 535/BOL.MD | 14/03/2024 | 13/05/2024 | TULIP ENTERPRISE | 5.41 | 0 | 0 | 30
5 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | WBSEDCL QUOTATION FOR SHANKARPUR WATER SUPPLY SCHEME |  |  | BILL/01832/2023-2024 | BP-23-24-259 | 06/02/2024 | 06/02/2024 | WBSEDCL | 21.4 | 0 | 0 | 0
6 | BIRBHUM | Rajnagar | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | New | Different works related to water supply scheme at SHANKARPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte.150 | AE | JE1 | ORD/000021/2023-2024 | 1094/BHM | 06/04/2023 | 01/10/2025 | SYED GOLAM ZILANI | 353.43 | 0 | 0 | 30
7 | BIRBHUM | Rajnagar | Bolpur Mechanical | Shankarpur Piped Water Scheme | SM/14082 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001240/2023-2024 | 534/BOL.MD | 14/03/2024 | 06/06/2025 | SINHA ELECTRICALS | 7.8 | 0 | 0 | 100
8 | BIRBHUM | Rajnagar | Birbhum Division | Shankarpur Piped Water Scheme | SM/14082 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 658.88 | 0 | 0