## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. | SM/14085 | New | Providing Electro-mechanical accessories and others for KHANPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000981/2023-2024 | 3296/Bol.MD | 29/09/2023 | 28/11/2023 | DEY ENTERPRISE | 27.42 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Birbhum Division | Khanpur Piped Water Supply Scheme. | SM/14085 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 1624/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 18.95 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. | SM/14085 | New | New service connection at Khanpur PWSS under Dubrajpur Block, under Bolpur Mech. Division,PHE. Dte. |  |  | BILL/02190/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. | SM/14085 | New | wbsedcl quotation for khanpur pump house no-i |  |  | BILL/02080/2023-2024 | BP-2023-24-288 | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.35 | 0 | 0 | 0
5 | BIRBHUM | Murarai-I | Birbhum Division | Khanpur Piped Water Supply Scheme. | SM/14085 | New | Different related to water supply scheme at KHANPUR, Harinduba & Abdullahapur and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE3 | ORD/000074/2023-2024 | 1344/BHM | 20/04/2023 | 01/08/2026 | M/S ELLIUS KHAN | 1347.61 | 187.67 | 13.93 | 30
Total | [13 empty] | 1400.67 | 187.67 | 13.4