## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1444/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 36.79 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Prayagpur PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001244/2023-2024 | 529/BOL.MD | 14/03/2024 | 13/05/2024 | SWAPAN ENTERPRISE | 7.62 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Prayagpur Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000509/2024-2025 | 3756/Bol.MD | 12/09/2024 | 12/10/2024 | M/S P.P ELECTRICALS | 25.25 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000842/2022-2023 | 333/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000843/2022-2023 | 437/RSD | 25/11/2022 | 09/01/2023 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 231/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 5.61 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Quotation money for new service connection at Prayagpur PWSS P/H- III under Mayureswar CCC |  |  | BILL/00822/2024-2025 | BP-24-25-183 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Different works related to Water Supply Scheme at PRAYAGPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000276/2023-2024 | 3596/BHM | 21/08/2023 | 11/11/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 516.3 | 0 | 0 | 55
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing Electro-mechanical accessories and others for Prayagpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000839/2023-2024 | 3278/Bol.MD | 29/09/2023 | 01/01/2026 | ORIENTAL ENGINEERING CO. | 55.59 | 0 | 0 | 50
Total | [13 empty] | 655.98 | 0 | 0