## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1444/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 36.79 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Prayagpur PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001244/2023-2024 | 529/BOL.MD | 14/03/2024 | 13/05/2024 | SWAPAN ENTERPRISE | 7.62 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Prayagpur Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000509/2024-2025 | 3756/Bol.MD | 12/09/2024 | 12/10/2024 | M/S P.P ELECTRICALS | 25.25 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000842/2022-2023 | 333/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000843/2022-2023 | 437/RSD | 25/11/2022 | 09/01/2023 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 231/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 5.61 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Quotation money for new service connection at Prayagpur PWSS P/H- III under Mayureswar CCC |  |  | BILL/00822/2024-2025 | BP-24-25-183 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Different works related to Water Supply Scheme at PRAYAGPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000276/2023-2024 | 3596/BHM | 21/08/2023 | 11/11/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 516.3 | 0 | 0 | 55
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing Electro-mechanical accessories and others for Prayagpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000839/2023-2024 | 3278/Bol.MD | 29/09/2023 | 01/01/2026 | ORIENTAL ENGINEERING CO. | 55.59 | 0 | 0 | 50
10 | BIRBHUM | Mayureswar-II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 723.83 | 0 | 0