## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Ninga Piped Water Supply Scheme | SM/14089 | New | Providing Electro-mechanical accessories and others for Ninga PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000477/2023-2024 | 2230/Bol.MD | 12/09/2023 | 11/11/2023 | DEY ENTERPRISE | 44.43 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1550/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 58.2 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Ninga Piped Water Supply Scheme | SM/14089 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ninga PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001252/2023-2024 | 527/BOL.MD | 14/03/2024 | 13/05/2024 | DIPALI CONSTRUCTION | 7.61 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000786/2022-2023 | 289/RSD | 31/08/2022 | 15/10/2022 | ECO CARE | 2.4 | 2.24 | 93.38 | 100
5 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000797/2022-2023 | 373/RSD | 22/09/2022 | 06/11/2022 | ECO CARE | 2.91 | 2.82 | 97.06 | 100
6 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Material Requisition To Resource Division |  |  | RTOR000047/2024-2025 | 3261/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 12.4 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Ninga & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUMDivision, PHE Dte | AE | JE,JE3 | ORD/000320/2024-2025 | 3116/BHM | 13/11/2024 | 13/11/2025 | M/S DATTA ENTERPRISE | 375.28 | 0 | 0 | 20
8 | BIRBHUM | Rampurhat-II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
Total | [13 empty] | 543.52 | 5.06 | 0.93