## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1550/BHM | 26/04/2023 |  | Resource Division | 58.2 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Ninga Piped Water Supply Scheme | SM/14089 | New | Providing Electro-mechanical accessories and others for Ninga PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000477/2023-2024 | 2230/Bol.MD | 12/09/2023 | 11/11/2023 | DEY ENTERPRISE | 44.43 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat - II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000786/2022-2023 | 289/RSD | 31/08/2022 | 15/10/2022 | ECO CARE | 2.4 | 2.24 | 93.38 | 100
4 | BIRBHUM | Rampurhat - II | Birbhum Division | Ninga Piped Water Supply Scheme | SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000797/2022-2023 | 373/RSD | 22/09/2022 | 06/11/2022 | ECO CARE | 2.91 | 2.53 | 87.05 | 100
5 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Ninga Piped Water Supply Scheme | SM/14089 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ninga PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001252/2023-2024 | 527/BOL.MD | 14/03/2024 | 13/05/2024 | DIPALI CONSTRUCTION | 7.61 | 0 | 0 | 0
Total | [13 empty] | 115.55 | 4.77 | 4.13