## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME | SM/14115 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1457/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 20.15 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME | SM/14115 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for HATKALUA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/001142/2021-2022 | 105/BSD | 21/03/2022 | 17/09/2022 | APEX ENGINEERING | 3.87 | 0 | 0 | 100
3 | BIRBHUM | Labpur | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME | SM/14115 | New | Different works related to water supply scheme at HATKALUA PIPED WATER SUPPLY SCHEME (TSM/016242) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000011/2023-2024 | 1096/BHM | 06/04/2023 | 02/10/2024 | M/S R B ENTERPRISE | 446.12 | 80.15 | 17.97 | 5
4 | BIRBHUM | Labpur | Bolpur Mechanical | HATKALUA PIPED WATER SUPPLY SCHEME | SM/14115 | New | Quotation for new service connection at Hatkaluha PWSS(P/H-I) |  |  | BILL/01023/2024-2025 | BP-24-25-275 | 06/12/2024 | 06/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.62 | 0 | 0 | 0
Total | [13 empty] | 478.76 | 80.15 | 16.74