## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Providing Electro-mechanical accessories and others for Kanksa PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000524/2023-2024 | 2155/Bol.MD | 28/08/2023 | 27/10/2023 | GOENKA ENTERPRISE | 44.03 | 18.79 | 42.69 | 50
2 | BIRBHUM | Mayureswar-I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Continuation Work Order for Preparation & Submission of DPR for (Kanska) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000631/2022-2023 | 230/RSD | 27/06/2022 | 25/09/2022 | ENVIROTECH SOLUTIONS | 2.86 | 2.33 | 81.28 | 100
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1447/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 5.45 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Supplly & delivery of pumping machinery Kanksa water supply scheme Block- Mayureswar-I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000004/2024-2025 | 690./AE-III | 08/04/2024 | 22/04/2024 | GOENKA ENTERPRISE | 1.48 | 1.48 | 100 | 100
5 | BIRBHUM | Mayureswar-I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 206/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 3.91 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | WBSEDCL QUOTATION FOR PURBA KANKSA P H NO II WS SCHEME |  |  | BILL/01789/2023-2024 | BP-23-24-256 | 06/02/2024 | 06/02/2024 | WBSEDCL | 5.76 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | WBSEDCL QUOTATION FOR KANKSA P H NO -2 WS SCHEME |  |  | BILL/01438/2023-2024 | BP-23-24-178 | 07/12/2023 | 07/12/2023 | WBSEDCL | 3.82 | 0 | 0 | 0
Total | [13 empty] | 67.3 | 22.6 | 33.58