## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1460/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 103.64 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Lachhiator PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001248/2023-2024 | 525/BOL.MD | 14/03/2024 | 13/05/2024 | ABHISEK ENGTNEERING CONCERN | 7.61 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE | JE3 | ORD/000806/2022-2023 | 295/RSD | 07/09/2022 | 06/12/2022 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE | JE3 | ORD/000807/2022-2023 | 403/RSD | 13/10/2022 | 11/01/2023 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-I | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 204/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 8.19 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | New service connection at Lachiatore PH-IV PWSS under Bol.MD, P.H.E Dte. |  |  | BILL/00824/2024-2025 | BP-24-25-185 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.14 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | WBSEDCL QUOTATION FOR LACHIATORE PIPED WS SCHEME PH NO.II |  |  | BILL/01881/2023-2024 | BP-23-24-282 | 22/02/2024 | 22/02/2024 | WBSEDCL | 2.54 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | WBSEDCL QUOTATION FOR LOCHIATORE PIPED WS SCHEME PH NO.I |  |  | BILL/01880/2023-2024 | BP-23-24-284 | 22/02/2024 | 22/02/2024 | WBSEDCL | 4.19 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | WBSEDCL QUOTATION FOR LACHIATOR W/S SCHEME PH-3 |  |  | BILL/02464/2023-2024 | BP-24-25-03 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-I | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 01/01/2026 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
11 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14125 | New | Providing Electro-mechanical accessories and others for Lachhiator PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000738/2023-2024 | 3479/Bol.MD | 07/11/2023 | 06/01/2024 | DEY ENTERPRISE | 65.96 | 0 | 0 | 80
Total | [13 empty] | 2209.22 | 0 | 0