## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 1540/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 51.95 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Additional work in connection with Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allieds works at Birchandrapur Piped Water Supply Scheme, Block-Mayureswar-I, under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/001210/2023-2024 | 372/BOL.MD | 06/03/2024 | 05/04/2024 | SARKAR ELECTRICAL | 18.22 | 0 | 0 | 77
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE | JE3 | ORD/000802/2022-2023 | 286/RSD | 29/08/2022 | 27/11/2022 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE | JE3 | ORD/000803/2022-2023 | 360/RSD | 20/09/2022 | 19/12/2022 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | New service connection charges at Birchandrapur PH-III PWSS. |  |  | BILL/00825/2024-2025 | BP-24-25-186 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Providing Electro-mechanical accessories and others for Birchandrapur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000734/2023-2024 | 3477/Bol.MD | 07/11/2023 | 01/07/2025 | EASTERN INDIA SALES & SERVICE | 67.61 | 0 | 0 | 60
7 | BIRBHUM | Mayureswar-I | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/14141 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2,JE3 | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 30/09/2025 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 0 | 20
Total | [13 empty] | 2220.14 | 0 | 0