## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Providing Electro-mechanical accessories and others for Sultanpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000836/2023-2024 | 3275/BOL.MD | 29/09/2023 | 28/11/2023 | M. S. ENTERPRISE | 67.76 | 0 | 0 | 40
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Sultanpur PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte.. | Assistant Engineer-III | Junior Engineer | ORD/001220/2023-2024 | 405/Bol.MD | 07/03/2024 | 21/04/2024 | SATYAJIT GHOSH | 25.78 | 0 | 0 | 40
3 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000844/2022-2023 | 334/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block | AE | JE3 | ORD/000845/2022-2023 | 438/RSD | 29/11/2022 | 13/01/2023 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 200/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 11.4 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | NEW SERVICE CONNECTION AT SULTANPUR PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION PHE Dte... |  |  | BILL/00022/2024-2025 | BP-24-25-09 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.36 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Quotation for new service connection at Sultanpur PWSS P/H- IV (Block- Mayureswar -II) |  |  | BILL/00156/2024-2025 | BP-2024-2025-80 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.56 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | New service connection at Sultanpur PWSS ( P/H- 3) |  |  | BILL/00112/2024-2025 | BP-2024-2025-51 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Quotation for New Service connection at Sultanpur PWSS P/H-3 (Bolck- Mayureswar-II) |  |  | BILL/00155/2024-2025 | BP-2024-2025-81 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.25 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Different works related to Water Supply Scheme at SULTANPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000161/2023-2024 | 2065/BHM | 08/06/2023 | 31/03/2026 | M/S.SUMAN CONSTRUCTION | 575.26 | 0 | 0 | 45
11 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 779.19 | 0 | 0