## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Different works related to Water Supply Scheme at SULTANPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000161/2023-2024 | 2065/BHM | 08/06/2023 | 31/03/2026 | M/S.SUMAN CONSTRUCTION | 575.26 | 95.97 | 16.68 | 45
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Providing Electro-mechanical accessories and others for Sultanpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000836/2023-2024 | 3275/BOL.MD | 29/09/2023 | 28/11/2023 | M. S. ENTERPRISE | 67.76 | 42.01 | 62 | 40
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Sultanpur PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte.. | Assistant Engineer-III | Junior Engineer | ORD/001220/2023-2024 | 405/Bol.MD | 07/03/2024 | 21/04/2024 | SATYAJIT GHOSH | 25.78 | 19.85 | 77.02 | 40
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000844/2022-2023 | 334/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.54 | 2.61 | 73.66 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block | AE | JE3 | ORD/000845/2022-2023 | 438/RSD | 29/11/2022 | 13/01/2023 | ENVIROTECH SOLUTIONS | 3.5 | 3.5 | 99.96 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 200/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 11.4 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | NEW SERVICE CONNECTION AT SULTANPUR PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION PHE Dte... |  |  | BILL/00022/2024-2025 | BP-24-25-09 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.36 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Quotation for new service connection at Sultanpur PWSS P/H- IV (Block- Mayureswar -II) |  |  | BILL/00156/2024-2025 | BP-2024-2025-80 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.56 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | New service connection at Sultanpur PWSS ( P/H- 3) |  |  | BILL/00112/2024-2025 | BP-2024-2025-51 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | SM/14160 | New | Quotation for New Service connection at Sultanpur PWSS P/H-3 (Bolck- Mayureswar-II) |  |  | BILL/00155/2024-2025 | BP-2024-2025-81 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.25 | 0 | 0 | 0
Total | [13 empty] | 711.35 | 163.94 | 23.05