## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Salan Piped Water Supply Scheme. | SM/14207 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 1364/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 19.72 | 0 | 0 | 0
Total | [13 empty] | 19.72 | 0 | 0