## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | New | Continuation Work Order for Preparation & Submission of DPR for (Singari) Water Supply Scheme under Mayureswar-II Development Block. | AE | JE3 | ORD/000629/2022-2023 | 222/RSD | 23/06/2022 | 07/08/2022 | ENVIROTECH SOLUTIONS | 2.86 | 2.38 | 83.04 | 100
2 | BIRBHUM | Mayureswar-II | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 1503/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 4.08 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | New | Providing Electro-mechanical accessories and others for Singari PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000837/2023-2024 | 3276/Bol.MD | 29/09/2023 | 28/11/2023 | PADMA ENGINEERING CO. | 33.06 | 7.1 | 21.47 | 30
4 | BIRBHUM | Mayureswar-II | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 2443/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 5.24 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/14208 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection, related to water supply scheme at Singari & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE3 | ORD/000100/2024-2025 | 2105/BHM | 29/07/2024 | 29/07/2025 | KAZI EMDADUL HAQUE | 270.02 | 0 | 0 | 30
Total | [13 empty] | 315.26 | 9.47 | 3