## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Barua Gopalpur Piped Water Supply Scheme. | SM/14421 | New | Different works related to water supply scheme at BARUA GOPALPUR & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE3 | ORD/000397/2023-2024 | 4162/BHM | 30/10/2023 | 30/07/2024 | SUNIL RABI DAS | 781.48 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Barua Gopalpur Piped Water Supply Scheme. | SM/14421 | New | Providing Electro-mechanical accessories and others for BARUA GOPALPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000884/2023-2024 | 3288/Bol.MD | 29/09/2023 | 28/11/2023 | PADMA ENGINEERING CO. | 45.96 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Birbhum Division | Barua Gopalpur Piped Water Supply Scheme. | SM/14421 | New | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 1579/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 155.49 | 0 | 0 | 0
Total | [13 empty] | 982.94 | 0 | 0