## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Providing Electro-mechanical accessories and others for Baraturigram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000735/2023-2024 | 3478/Bol.MD | 07/11/2023 | 06/01/2024 | R. N. S. TRADING | 66.79 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-I | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1543/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 222.46 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-C) under Mayureswar-I Development Block. | AE | JE3 | ORD/000831/2022-2023 | 443/RSD | 02/12/2022 | 02/03/2023 | ENVIROTECH SOLUTIONS | 2.22 | 1.21 | 54.78 | 100
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE | JE3 | ORD/000829/2022-2023 | 310/RSD | 08/09/2022 | 07/12/2022 | ENVIROTECH SOLUTIONS | 3.58 | 3.56 | 99.44 | 100
5 | BIRBHUM | Mayureswar-I | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE | JE3 | ORD/000830/2022-2023 | 422/RSD | 03/11/2022 | 01/02/2023 | ENVIROTECH SOLUTIONS | 3.29 | 3.23 | 98.07 | 100
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Supply, delivery & Installation of Submersible Pumping Machinery and other allied work for newly sunk T/W at Baraturigram water supply scheme(Block-Mayureswar-I) under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001202/2023-2024 | 369/BOL.MD | 06/03/2024 | 05/04/2024 | RAJIB GHOSH | 8.79 | 8.41 | 95.74 | 100
7 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Baraturigram Piped water supply scheme(PH-III) under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001204/2023-2024 | 370/BOL.MD | 06/03/2024 | 05/04/2024 | MASSK ENGINEERING WORKS | 7.19 | 6.99 | 97.33 | 100
8 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Quotation for new service connection at Baraturigram PWSS P/H -III under Mayureswar ccc (Block-Mayureswar -I) |  |  | BILL/00952/2024-2025 | BP-2024-25-260 | 18/11/2024 | 18/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | New service connection for Baraturigram PH-I Water supply scheme under Bolpur Mechanical Division, P.H.E Dte. |  |  | BILL/01089/2024-2025 | BP-24-25-282 | 17/12/2024 | 17/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-I | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2,JE3 | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 30/09/2025 | B RAI CONSTRUCTION COMPANY | 2071.77 | 106.89 | 5.16 | 20
11 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Supply & delivery of different electrical accessories at Baraturigram Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000510/2024-2025 | 3757/Bol.MD | 12/09/2024 | 08/02/2025 | SUNIL RABIDAS | 36.82 | 0 | 0 | 100
12 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | SM/14424 | New | Quotation for new service connection at Baraturigram PWSS P/H-IV (Vill- Gopalnagar) at Block- Mayureswar-I under Mayureswar CCC |  |  | BILL/01182/2024-2025 | BP-24-25-317 | 22/01/2025 | 22/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.15 | 0 | 0 | 0
Total | [13 empty] | 2442.63 | 130.29 | 5.33