## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | New | Different works related to water supply scheme at MONACHITURA PIPED WATER SUPPLY SCHEME (TSM/017000) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE3 | ORD/000366/2024-2025 | 3155/BHM | 19/11/2024 | 19/11/2025 | M/S TAPAS KUMAR CHAKRABORTY | 574 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | New | Preparation & Submission of Detail Project Report (DPR) for MONACHITURA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/001135/2021-2022 | 100/BSD | 15/03/2022 | 11/09/2022 | APEX ENGINEERING | 4.92 | 4.39 | 89.13 | 100
3 | BIRBHUM | Labpur | Bolpur Mechanical | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Mona Chaitura PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001130/2024-2025 | 332/BOL.MD | 19/02/2025 | 19/06/2025 | OSMAN SEKH | 76.25 | 0 | 0 | 50
Total | [13 empty] | 655.17 | 4.39 | 0.67