## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Providing Electro-mechanical accessories and others for Albandha & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2023-2024 | 2238/BOL.MD. | 13/09/2023 | 12/12/2023 | DEY ENTERPRISE | 73.35 | 35 | 47.72 | 50
2 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1547/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 219.35 | 0 | 0 | 0
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Supply and delivery of 80 mm UPVC standard type column pipe (Cream colour) for albandha water supply scheme(T/W-II) under BOL MD, PHE Dte.. | Assistant Engineer (HQ) | Junior Engineer | ORD/000815/2024-2025 | 4195/BOL.MD | 22/10/2024 | 11/11/2024 | M. S. ENTERPRISE | 2.6 | 0 | 0 | 100
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Supply and delivery of column pipe for albandha water supply scheme(T/W-I) under BOL MD, PHE Dte.. | Assistant Engineer (HQ) | Junior Engineer | ORD/000550/2024-2025 | 3805/BOL.MD | 12/09/2024 | 02/10/2024 | SATYAJIT GHOSH | 2.52 | 2.52 | 100 | 100
5 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Supply and delivery of Submersible pump for albandha Water Supply under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000552/2024-2025 | 3806/BOL.MD | 12/09/2024 | 02/10/2024 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.48 | 1.12 | 45.12 | 100
6 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Supply & delivery of submersible cable accessories at albandha Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000572/2024-2025 | 3843/BOL.MD | 18/09/2024 | 08/10/2024 | UNITED TRADERS | 2.15 | 2.15 | 100 | 100
7 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | WBSEDCL QUOTATION FOR ALBANDHA WS SCHEME |  |  | BILL/01591/2023-2024 | BP-23-24-221 | 15/01/2024 | 15/01/2024 | WBSEDCL | 5.28 | 0 | 0 | 0
8 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | AE | JE4 | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 01/01/2026 | AMAL DUTTA ROY | 1648.21 | 193.7 | 11.75 | 12
9 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025. | Assistant Engineer | JE3 | ORD/000543/2024-2025 | 1237/BSD | 31/12/2024 | 30/06/2025 | RAJIYA BIBI | 0.85 | 0 | 0 | 0
10 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Albandha Piped Water Supply Scheme. | SM/14533 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000054/2024-2025 | 378/CMSD-I | 24/12/2024 | 24/06/2025 | SUJATA BHOWMICK | 0.86 | 2.15 | 248.85 | 0
11 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Continuation work order for "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025" for another 03(Three) months i.e. 01.07.2025 to 30.09.2025. | Assistant Engineer | JE3 | ORD/000095/2025-2026 | 640/BSD | 20/06/2025 | 20/09/2025 | RAJIYA BIBI | 0.43 | 0 | 0 | 0
12 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Supply & delivery of different electrical accessories at albandha Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000555/2024-2025 | 3841/BOL.MD | 18/09/2024 | 08/10/2024 | SUNIL RABIDAS | 2.95 | 2.95 | 100 | 100
13 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Albandha Piped Water Supply Scheme. | SM/14533 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 17.25 | 0.08 | 11
Total | [13 empty] | 23300.8 | 256.84 | 1.1